## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 / Sprint 1-2 |  | US-01 | As a Product Manager, I want the system foundation, feedback ingestion, preprocessing and categorization to be established so that customer feedback is ready for analysis. | MUST | — | Ankitha, Alvin, Vidheendhu | Not Started
Milestone 2 / Sprint 3-4 |  | US-02 | As a Product Manager, I want customer feedback to be analyzed for themes, pain points, feature groups and trends and displayed through dashboards so that I can identify actionable product insights. | MUST | US-01 | Ankitha, Alvin, Vidheendhu | Not Started
Milestone 3 / Sprint 5-6 |  | US-03 | As a Product Manager, I want AI to generate PRDs, user stories and acceptance criteria, prioritize features and support product-related queries so that product planning becomes faster and more data-driven. | MUST | US-02 | Ankitha, Alvin | Not Started
Milestone 4 / Sprint 7-8 |  | US-04 | As a Product Manager, I want roadmap planning, milestone recommendations, executive reports and final quality evaluation so that product insights can be converted into actionable product plans. | MUST | US-03 | Ankitha, Alvin | Not Started
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILESTONE 1 / SPRINT 1-2 BACKLOG
US-01 | S1-T01 | Study product-management workflows and identify system requirements |  |  | Ankitha | Analysis | Not Started | 4
US-01 | S1-T02 | Define functional and non-functional system requirements |  |  | Ankitha | Analysis | Not Started | 5
US-01 | S1-T03 | Design overall system architecture |  |  | Vidheendhu | Design | Not Started | 6
US-01 | S1-T04 | Design database schema and core data entities |  |  | Vidheendhu | Design | Not Started | 5
US-01 | S1-T05 | Design customer-feedback data pipeline |  |  | Vidheendhu | Design | Not Started | 5
US-01 | S1-T06 | Define supported feedback, review and support-ticket input formats |  |  | Ankitha | Analysis | Not Started | 3
US-01 | S1-T07 | Implement customer feedback import workflow |  |  | Ankitha | Development | Not Started | 8
US-01 | S1-T08 | Implement review/support-ticket import workflow |  |  | Ankitha | Development | Not Started | 8
US-01 | S1-T09 | Implement uploaded-data validation |  |  | Ankitha | Development | Not Started | 6
US-01 | S1-T10 | Test data ingestion with representative inputs |  |  | Ankitha | Testing | Not Started | 5
US-01 | S2-T01 | Implement data cleaning workflow |  |  | Alvin | Development | Not Started | 8
US-01 | S2-T02 | Implement data preprocessing workflow |  |  | Alvin | Development | Not Started | 8
US-01 | S2-T03 | Implement feedback categorization workflow |  |  | Alvin | Development | Not Started | 8
US-01 | S2-T04 | Validate cleaned and categorized output |  |  | Alvin | Testing | Not Started | 6
US-01 | S2-T05 | Document Milestone 1 pipeline and setup |  |  | Alvin | Documentation | Not Started | 4
MILESTONE 2 / SPRINT 3-4 BACKLOG
US-02 | S3-T01 | Define theme extraction requirements |  |  | Ankitha | Analysis | Not Started | 3
US-02 | S3-T02 | Implement recurring-theme extraction |  |  | Ankitha | AI/ML | Not Started | 8
US-02 | S3-T03 | Implement customer pain-point identification |  |  | Ankitha | AI/ML | Not Started | 8
US-02 | S3-T04 | Aggregate theme and pain-point results |  |  | Alvin | Data Processing | Not Started | 5
US-02 | S3-T05 | Test theme and pain-point outputs |  |  | Alvin | Testing | Not Started | 5
US-02 | S4-T01 | Prepare feature-request representations for grouping |  |  | Alvin | AI/ML | Not Started | 6
US-02 | S4-T02 | Implement feature-request clustering |  |  | Alvin | AI/ML | Not Started | 8
US-02 | S4-T03 | Implement trend-analysis workflow |  |  | Ankitha | Development | Not Started | 8
US-02 | S4-T04 | Design dashboard insight views |  |  | Vidheendhu | Design | Not Started | 4
US-02 | S4-T05 | Implement categorized-feedback and insight dashboard |  |  | Vidheendhu | Frontend | Not Started | 8
US-02 | S4-T06 | Connect dashboard to backend insight results |  |  | Vidheendhu | Integration | Not Started | 6
US-02 | S4-T07 | Define evaluation criteria for issue detection and feature grouping |  |  | Vidheendhu | Analysis | Not Started | 3
US-02 | S4-T08 | Validate issue detection and feature grouping accuracy |  |  | Vidheendhu | Testing | Not Started | 8
US-02 | S4-T09 | Document Milestone 2 analysis and validation results |  |  | Vidheendhu | Documentation | Not Started | 4
MILESTONE 3 / SPRINT 5-6 BACKLOG
US-03 | S5-T01 | Define PRD generation inputs, sections and output requirements |  |  | Alvin | Analysis | Not Started | 4
US-03 | S5-T02 | Design context and prompt structure for PRD generation |  |  | Alvin | AI/ML | Not Started | 5
US-03 | S5-T03 | Integrate Generative AI capability |  |  | Alvin | AI Integration | Not Started | 8
US-03 | S5-T04 | Implement PRD generation workflow |  |  | Alvin | Development | Not Started | 8
US-03 | S5-T05 | Implement PRD output display/preview |  |  | Alvin | Frontend | Not Started | 6
US-03 | S5-T06 | Test generated PRDs for completeness and consistency |  |  | Alvin | Testing | Not Started | 6
US-03 | S6-T01 | Define user-story and acceptance-criteria output format |  |  | Ankitha | Analysis | Not Started | 3
US-03 | S6-T02 | Implement automatic user-story generation |  |  | Ankitha | AI Integration | Not Started | 7
US-03 | S6-T03 | Implement acceptance-criteria generation |  |  | Ankitha | AI Integration | Not Started | 6
US-03 | S6-T04 | Define configurable feature-prioritization factors |  |  | Ankitha | Analysis | Not Started | 4
US-03 | S6-T05 | Implement feature-prioritization scoring workflow |  |  | Ankitha | Development | Not Started | 8
US-03 | S6-T06 | Validate feature-priority results |  |  | Ankitha | Testing | Not Started | 5
US-03 | S6-T07 | Define product-related conversational query use cases |  |  | Alvin | Analysis | Not Started | 3
US-03 | S6-T08 | Implement conversational product-query interface/workflow |  |  | Alvin | AI Integration | Not Started | 10
US-03 | S6-T09 | Test conversational responses against representative queries |  |  | Alvin | Testing | Not Started | 6
MILESTONE 4 / SPRINT 7-8 BACKLOG
US-04 | S7-T01 | Define roadmap planning inputs and timeline structure |  |  | Ankitha | Analysis | Not Started | 4
US-04 | S7-T02 | Design milestone recommendation logic |  |  | Ankitha | Design | Not Started | 5
US-04 | S7-T03 | Implement roadmap planning workflow |  |  | Ankitha | Development | Not Started | 8
US-04 | S7-T04 | Implement milestone recommendation feature |  |  | Ankitha | Development | Not Started | 7
US-04 | S7-T05 | Implement roadmap visualization |  |  | Ankitha | Frontend | Not Started | 8
US-04 | S7-T06 | Define executive-summary and product-strategy report structure |  |  | Alvin | Analysis | Not Started | 3
US-04 | S7-T07 | Implement executive-summary generation |  |  | Alvin | AI Integration | Not Started | 7
US-04 | S7-T08 | Implement product-strategy report generation |  |  | Alvin | AI Integration | Not Started | 8
US-04 | S7-T09 | Test roadmap and generated reports |  |  | Alvin | Testing | Not Started | 6
US-04 | S8-T01 | Prepare end-to-end testing plan |  |  | Ankitha & Alvin | Testing | Not Started | 5
US-04 | S8-T02 | Run functional and integration testing |  |  | Ankitha & Alvin | Testing | Not Started | 8
US-04 | S8-T03 | Evaluate AI output quality |  |  | Ankitha & Alvin | Evaluation | Not Started | 8
US-04 | S8-T04 | Fix high-priority defects |  |  | Ankitha & Alvin | Development | Not Started | 10
US-04 | S8-T05 | Optimize system and output quality |  |  | Ankitha & Alvin | Optimization | Not Started | 8
US-04 | S8-T06 | Prepare technical documentation and final report |  |  | Ankitha & Alvin | Documentation | Not Started | 8
US-04 | S8-T07 | Prepare final demonstration and presentation |  |  | Ankitha & Alvin | Documentation | Not Started | 6
US-04 | S8-T08 | Perform final project readiness check |  |  | Ankitha & Alvin | Release | Not Started | 5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1
2 | Sprint 2
3 | Sprint 3
4 | Sprint 4
5 | Sprint 5
6 | Sprint 6
7 | Sprint 7
8 | Sprint 8