## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Development Team | Not recorded | GET /clusters returned HTTP 500 because cluster_labels was a list while the route expected a dictionary and called .items(). | Sprint 4 | Backend Team | Logical | Inspected the traceback in routes/clusters.py and corrected the cluster-label handling so the endpoint works with the actual returned data structure. | Not recorded | Closed | Verified that /clusters responds successfully after the correction.
2 | Development Team | Not recorded | Backend failed to start when user_stories.py imported 'from google import genai', producing ImportError: cannot import name 'genai'. | Sprint 6 | Backend Team | Logical | Aligned the user-story generator with the installed Google GenAI SDK/import pattern and verified application startup. | Not recorded | Closed | The Uvicorn application started successfully after the import issue was resolved.
3 | Development Team | Not recorded | Product Roadmap and Product Strategy Reports cards were visible in the dashboard but clicking them did not navigate to their respective pages. | Sprint 8 | Frontend Team | User Interface | Reworked Product Management Tools navigation to use explicit Next.js routes for /roadmap and /strategy. | Not recorded | Closed | The individual /roadmap and /strategy pages were confirmed to load successfully.
4 | Development Team | Not recorded | Strategy page showed a module import/type-resolution error for '@/components/product-modules/StrategyReports'. | Sprint 8 | Frontend Team | Maintainability | Created/placed StrategyReports.tsx at the expected components/product-modules path and aligned the default export with the page import. | Not recorded | Closed | The Strategy page compiled and loaded after the component path/export was corrected.
5 | Development Team | Not recorded | RICE score was displayed as N/A in the Feature Prioritization UI even though backend prioritization was generating numeric RICE values. | Sprint 7 | Frontend Team | User Interface | Checked the frontend API response mapping and aligned the UI field names with the backend rice_score property. | Not recorded | Closed | RICE values are now displayed from the backend prioritization response.
6 | Development Team | Not recorded | AI Copilot could take unnecessarily long for a simple greeting such as 'Hi' because the normal dataset/context and LLM flow was triggered. | Sprint 6 | AI/Backend Team | Logical | Added lightweight greeting handling so simple greetings do not unnecessarily trigger the full dataset analysis and Gemini generation flow. | Not recorded | Closed | Simple greetings now receive a short response without an unrelated dataset summary.
7 | Development Team | Not recorded | AI Copilot responses to general prompts could include a full dataset summary instead of answering only the question asked. | Sprint 6 | AI/Backend Team | Logical | Refined the Copilot prompt to answer the exact user question, avoid unrelated summaries, and use dataset context only when relevant. | Not recorded | Closed | Copilot responses are more focused and context-aware.
8 | Development Team | Not recorded | Raw Markdown symbols such as ## and ** could appear in Copilot headings/text when the response was rendered without appropriate formatting. | Sprint 6 | Frontend/AI Team | User Interface | Improved Markdown rendering and prompt formatting so headings, lists and bold text are rendered as formatted content instead of exposed Markdown symbols. | Not recorded | Closed | Copilot output now presents cleaner headings, alignment and emphasis.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others